## Changes
| Canvey Issues |  |  | Total=14 | On Queue=1 | Correction=2
|  |  |  | In Progress=0 | In Review=0 | Done=11
SL | Type | Platform | Tasks | Priority | Status | Screenshots | Note
1 | Correction | Website | Design | Normal | Done | https://prnt.sc/KceN5jflQz2T
2 | Bug | Website | It should keep same margin on top | Normal | Done | https://prnt.sc/WnSpXO6rmqqs
3 | Bug | Website | PIN should be 4 digit | Normal | Done | https://prnt.sc/6cOCs2DgILGD
4 | Improvement | Admin | Remove all of the dropping time | Normal | In revision | https://prnt.sc/9FzH4-ESCmRj https://prnt.sc/EjE-kDgnBcig https://prnt.sc/Y21ALVGmFQ5i
5 | Bug | Website | User & Password suggestion need to hide | Normal | Done | https://prnt.sc/6GxPkUjEQh2C
6 | Bug | Website | Remove editable mode | Normal | Done | https://prnt.sc/HVx8fLEv_ylo https://prnt.sc/gYx_mQyXc72K
7 | Bug | Website | Loader missing. Check all of the page for loader | Normal | Done | https://prnt.sc/c6yv1flQ_YvD
8 | Bug | Website | 4 digit PIN | Normal | Done | https://prnt.sc/zdudq_xZo2ca
9 | Bug | Website | Resent OTP missing | Normal | In revision | https://prnt.sc/vuFqj_vTnYDd
10 | Bug | Website | Rename to Reset OTP | Normal | Done | https://prnt.sc/aMLhZWmN4CtH
11 | Bug | Website | It should be "Your PIN reset OTP is .." | Normal | On queue | https://prnt.sc/6Z7k5FxJkd9I
12 | Bug | Website | Disable the suggestion | Normal | Done | https://prnt.sc/OzCbCz5jFQaW
13 | Bug | Website | The profile number is +880 but it's showing +44 in ticket page | Normal | Done | https://prnt.sc/qM3q_juH2UXR https://prnt.sc/UU5ph4tmDnPq
14 | Bug | Website | Need to know the exact reason. It working fine without login | Normal | Done | https://prnt.sc/al3XaoaeFAeG
https://prnt.sc/al3XaoaeFAeG

## Tables
Type | Priority | Status | Platform
Typo | Normal | On queue | Admin
Correction | Medium | In progress | Counter
Content | High | In review | Agent app
Feature |  | In revision | Android app
Bug |  | Done | iOS app
Broken Link |  |  | Website
New Task |  |  | Parcel
Improvement |  |  | Driver App
All

## Update Changes
| Canvey Issues |  |  | Total=10 | On Queue=10 | Correction=0
|  |  |  | In Progress=0 | In Review=0 | Done=0
SL | Type | Platform | Tasks | Priority | Status | Screenshots | Note
1 | Correction | Website | Credit payment show default "user name" in Mobile filed and "user pass" in PIN field after click on "Credit" pay, Should remove this default showing | Normal | On queue | https://prnt.sc/AqlvV-PFUOZ5
2 | New Task | Website | Keep Eye Button Besides Pin Number | Normal | On queue | https://prnt.sc/K6gfbb525ISA
3 | Correction | Website | Invalid suggestion need to hide from this pages -- | Normal | On queue | https://prnt.sc/NRTgHTl2EhKz https://prnt.sc/Ez4ch7q6Liv9 https://prnt.sc/9ZW2cr_V3AOu https://prnt.sc/QDRTBFM1KClv
4 | Correction | Website | Remove this default taking character (user) from PIN field | Normal | On queue | https://prnt.sc/mP1unU8eVfNc https://prnt.sc/Si5ADRLnFhPA
5 | Bug | Website | Don't show any error message after put invalid PIN | Normal | On queue | https://prnt.sc/qycJc0cORNJE
6 | Correction | Website | Route & Number of Seat(s)is not showing correctly | Normal | On queue | https://prnt.sc/kULLD3Be4igZ
7 | Bug | Website | Departure time is 07:00 AM, Reporting time is 06:30 AM , but in customer profile "My booking" section it shows incorrect time | Normal | On queue | https://prnt.sc/IIn0lvjnTf_Q https://prnt.sc/VOYZ--_CPwKS
8 | Correction | Website | Default invalid PIN show & also suggestion | Normal | On queue | https://prnt.sc/TlUpcKY8gAmY
9 | Correction | Website | Design issue | Normal | On queue | https://prnt.sc/1oI5UKSvuOSz
10 | New Task | Website | Keep the eye button close when password is showing | Normal | On queue | https://prnt.sc/bF7VkamnsVYp https://prnt.sc/cy3PT9ekskX6