## Admin Issues
| Rakaab Report Issues (Admin Panel) |  |  |  | Total=6 | On Queue=2 | Correction=0
[5 empty] | In Progress=0 | In Review=0 | Done=4 | Done=0
SL | Type | Page | Platform | Tasks | Priority | Status | Screenshots | Issue for | Developer | Note | Comments
| Correction | Parcel And Ticket Sales Report | Admin | When search for (ticket or parcel) filter then it's loading (uploded beta) | Normal | Done | https://prnt.sc/-OQOi1mY0vNJ https://prnt.sc/8-9zA1Cw4H1L | Backend | None | mdl=parcel_ticket_sales_report
| Improvement | Cash Flow | Admin | Specifically not showing parcel details, Head name can be rename by Parcel when it shows parcel details | Normal | Done | https://prnt.sc/p7DZJqHaNfDj https://prnt.sc/OGbcujRP9g8F | Backend | None | mdl=cash_flow
| Correction | Sales Report | Admin | Sales report not showing when specific select 3 filter ( User, Counter, Route ) in Rakaab Main | Normal | Done | https://prnt.sc/QOhSI_pOnamJ | Backend | None | mdl=rtWiseSaleReport
| New Task | Route wise sales report | Admin | Route name is not showing | Normal | On queue | https://prnt.sc/kRSjL1t-cf4u | Backend | None | mdl=routeWiseSummaryReport
| Correction | Counter Summary Report | Admin | "All users" wise counter summary report showing incorrectly in Rakaab Beta | Normal | On queue | https://prnt.sc/xSww42AGbNGv https://prnt.sc/_C6TIC3rkPsw | Backend | None | mdl=counterSummaryReport
| Correction | Parcel Counter User Report | Admin | Parcel received (view) is not showing any data in "Parcel counter user report" in rakaab main | Normal | Done | https://prnt.sc/aBOgZxH8sB72 | Backend | None | mdl=parcel_user_report
[8 empty] | Backend | None
[8 empty] | Backend | None
[8 empty] | Backend | None
[8 empty] | Backend | None

## Counter Panel
| Rakaab Currency Issues ( Counter Panel ) |  |  |  | Total=1 | On Queue=1 | Correction=0
[5 empty] | In Progress=0 | In Review=0 | Done=0
SL | Type | Page | Platform | Tasks | Priority | Status | Screenshots | Developer | Issue for | Note
1 | Correction | My sales | Counter | Single ticket sale with discount, it shows incorrect value to ticket price | Normal | On queue | https://prnt.sc/9myyCyWn1FaC | None | Backend
| Correction | Dispatch > Parcel cancel | Counter | Any parcel cancel request send to admin can be added here | Normal | On queue | https://prnt.sc/KEdcViaLAt7T | None | Backend
| Correction |  | Counter

## Tables
Type | Priority | Status | Platform | Developer
Typo | Normal | On queue | Admin | Abdus Salam
Correction | Medium | In progress | Counter | Shozol Khan
Content | High | In review | Agent app | Moinul Islam
Feature | Low | In revision | Android app | Mamun Hossen
Bug |  | Done | iOS app | Mehedi Hasan
Broken Link |  | Doing in future | Website | Rahat Rahman
New Task |  | Partially Done | Parcel | Rakibur Islam
Improvement |  |  | Driver App | Rashedul
|  |  | All | Smrity
Ikram Hossen
Shohel Rana
None