## 26-02-2024
| Rakaab Parcel Issues (26-02-2024) |  |  | Total=9 | On Queue=3 | Correction=0
|  |  |  | In Progress=0 | In Review=6 | Done=0 | Done=0
SL | Type | Platform | Tasks | Priority | Status | Screenshots | Note
1 | Bug | Agent app | This parcel is missing in statement, cash flow. This parcel has been added from agent app | Normal | In review | https://prnt.sc/PsydssNlbmYE https://prnt.sc/CKI7wcNbP7Fy https://prnt.sc/SjXcoMQc4wWU
2 | Bug | Agent app | When filtering using USD the parcel price is showing ETB's. This parcel added from agent app | Normal | In review | https://prnt.sc/6HZ-_lk6C2lM https://prnt.sc/M9n727dPVAGP
3 | Bug | Agent app | Still the parcel id isn't updated one. Counter and agent app both are same | Normal | In review | https://prnt.sc/CdGdOA6ogk1s https://prnt.sc/RlhqZhPmVf0O
4 | Bug | Agent app | Why the amount is showing different? | Normal | In review | https://prnt.sc/H37pqTB-n0Tw
5 | Bug | Agent app | Need to review parcel design | Normal | On queue | https://prnt.sc/0S7h8Hq7bg84 | Design Issue
6 | Bug | Agent app | Parcel And Ticket Sales Report isn't showing amount also showing wrong value in summary mode. Currency issue | Normal | In review | https://prnt.sc/BKjJtlEdIumE https://prnt.sc/vD3mF92Y0EdV
7 | Bug | Agent app | Showing all of the operator's counter | Normal | In review | https://prnt.sc/QH8P0yDzd5j6
8 | Bug | Counter | Need to fix the alignment | Normal | On queue | https://prnt.sc/CBzfJmwXThPw | Design Issue
| Bug | Agent app |  | Normal | On queue

## Changes
| Rakaab Parcel Issues(22-02-2024) |  |  | Total=22 | On Queue=2 | Correction=1
|  |  |  | In Progress=0 | In Review=18 | Done=1 | Done=0
SL | Type | Platform | Tasks | Priority | Status | Screenshots | Note
1 | Correction | Agent app | Rename search departure to Search Departure in Select Departure Page | Normal | In review
2 | Correction | Agent app | Need search on Departure assign | Normal | In review
3 | Correction | Agent app | Assin In departure show fleet, driver and coach name | Normal | In review
4 | Correction | Agent app | Assin in departure showing invalid departure | Normal | In review | https://prnt.sc/OfoVbnvbNnHd
5 | Correction | Agent app | Currency need to show in every amount | Normal | On queue |  | Backend Issue
6 | Correction | Agent app | Parcel sheet. without date all will be optional on the filter | Normal | In review | https://prnt.sc/YstKDp_riC9F
7 | Correction | Agent app | Rename Select Fleet to Parcel Fleet, keep only one day range and auto call | Normal | In review | https://prnt.sc/7l6uGyQMn5Oy
8 | Correction | Agent app | Parcel Search with mobile number | Normal | In review | https://prnt.sc/NWeL24d4b6eU | Backend issue
9 | Correction | Agent app | Dashboard count | Normal | On queue |  | Backend issue
10 | Correction | Agent app | Rename status On way to On the way | Normal | In review |  | Backend issue
11 | Correction | Agent app | Give a reload after parcel any status action | Normal | In review
12 | Correction | Agent app | P. Status showing wrong in Received list | Normal | In review | https://prnt.sc/4MHyebSh-AMn
13 | Correction | Agent app | Rename .... deliver the parcel | Normal | In review
14 | Correction | Agent app | My parcel need to add in more section foillow counter my parcel list | Normal | In review |  | Backend+App
15 |  |  | Parcel missing on Cash flow | Normal | In revision | https://prnt.sc/7jXb96VvvX9o | Backend issue
16 |  |  | Parcel amount and count missing on details mode |  | Done | https://prnt.sc/sAg1Y7BunBjC | Backend issue
17 |  |  | Amount isn't showing on pay type and amount field |  | In review | https://prnt.sc/da9w48BdsOcu | Backend issue | Backend issue
18 |  | Admin | Parcel related all report brand wise | Normal | In review |  | Backend issue
19 |  | Admin | Route wise parcel report | Normal | In review |  | Backend issue
20 |  | Admin | Phone number wise Parcel Counter User Report needed | Normal | In review | parcel_customer_report | Backend issue
21 |  | Counter | Parcel not add in "My transaction" | Normal | In review |  | Backend issue
22 |  | Counter | Currency issue in My Sales | Normal | In review |  | Backend issue
Normal

## Tables
Type | Priority | Status | Platform
Typo | Normal | On queue | Admin
Correction | Medium | In progress | Counter
Content | High | In review | Agent app
Feature |  | In revision | Android app
Bug |  | Done | iOS app
Broken Link |  |  | Website
New Task |  |  | Parcel
Improvement |  |  | Driver App
All